## 📊 SkoolTrack Pro SaaS — Development Work Plan

| 📦 Module | 📅 Estimated Time | ⚙️ Key Deliverables | 📝 Dependencies |
| --- | --- | --- | --- |
| 1. SaaS Multi-Tenancy Setup | 1 week | Multi-tenant architecture, database isolation, school onboarding API | None (foundation) |
| 2. User Management & Roles | 1 week | Role-based access, user CRUD, permissions setup | Depends on multi-tenancy setup |
| 3. Fees Structure & Vote Heads | 1 week | Fee structure CRUD, term-year setup, vote head management | User management |
| 4. Payment Integrations (MPESA & Bank) | 2 weeks | M-PESA Daraja API integration, Cario/Bank reconciliation APIs | Fees structure, user accounts |
| 5. Payment Transactions & Receipting | 1 week | Payment logging, fee balance computation, SMS payment notifications | Payment integrations |
| 6. Transport Management Module | 1 week | Routes, vehicles, student allocations, transport fee automation | Fees structure |
| 7. Procurement & Inventory | 2 weeks | Suppliers, POs, stock management, uniform issuance with fee debits | Fees module |
| 8. Exam Management Module | 2 weeks | Exam timetables, marks entry, report generation, position analysis | Student records, term setup |
| 9. Payroll & HR Module | 2 weeks | Employee records, payroll processing, deductions, payslip reports | User management |
| 10. Academic Records & Student Info | 1 week | Admissions, biodata, class allocation, status changes | User management |
| 11. SMS/Email Notification System | 1 week | Integrate Africa’s Talking API, messaging templates, logs | Multi-tenant, payment, exams |
| 12. Reporting & Dashboards | 2 weeks | Real-time dashboards, fee statements, collection summaries, exam analytics | All operational modules |
| 13. SaaS Admin Control Panel | 1 week | Manage schools, API keys, modules per school, logs | Multi-tenancy complete |